## Project Schedule
Phase | Task | Start Date | End Date | Duration (days) | Owner
M1 | User identification and stakeholder analysis | 2026-06-18 | 2026-06-20 | 3 | Team
M1 | User research and pain-point analysis | 2026-06-21 | 2026-06-24 | 4 | Team
M1 | Finalize SMART user stories | 2026-06-25 | 2026-06-28 | 4 | Team
M2 | Refine and assign user story IDs | 2026-06-29 | 2026-07-02 | 4 | Team
M2 | Create and prioritize product backlog | 2026-07-02 | 2026-07-04 | 3 | Team
M2 | Configure Jira board and workflow | 2026-07-03 | 2026-07-05 | 3 | Team
M2 | Prepare overall project schedule | 2026-07-04 | 2026-07-07 | 4 | Team
M2 | Prepare sprint and iteration schedule | 2026-07-05 | 2026-07-08 | 4 | Team
M2 | Design system components | 2026-07-05 | 2026-07-09 | 5 | Design Team
M2 | Create UML class diagram | 2026-07-07 | 2026-07-11 | 5 | Design Team
M2 | Create database / ER design | 2026-07-08 | 2026-07-12 | 5 | Database Team
M2 | Define frontend page and route architecture | 2026-07-09 | 2026-07-11 | 3 | Frontend Team
M2 | Develop common UI pages | 2026-07-10 | 2026-07-14 | 5 | Frontend Team
M2 | Develop resident UI pages | 2026-07-12 | 2026-07-17 | 6 | Frontend Team
M2 | Develop manager UI pages | 2026-07-13 | 2026-07-18 | 6 | Frontend Team
M2 | Develop maintenance staff UI pages | 2026-07-14 | 2026-07-18 | 5 | Frontend Team
M2 | Connect Vue routes and redirections | 2026-07-17 | 2026-07-19 | 3 | Frontend Team
M2 | UI review and frontend testing | 2026-07-19 | 2026-07-20 | 2 | Team
M2 | Document scrum meeting minutes | 2026-07-05 | 2026-07-20 | 16 | Scrum Master
M2 | Prepare frontend README | 2026-07-20 | 2026-07-20 | 1 | Frontend Team
M2 | Compile Milestone 2 PDF report | 2026-07-19 | 2026-07-21 | 3 | Documentation Team
M2 | Package and validate submission | 2026-07-21 | 2026-07-22 | 2 | Team
Sprint 1 | Implement authentication and role APIs | 2026-07-23 | 2026-07-26 | 4 | Backend Team
Sprint 1 | Implement complaint management APIs | 2026-07-24 | 2026-07-28 | 5 | Backend Team
Sprint 1 | Implement assignment and work-status APIs | 2026-07-27 | 2026-07-30 | 4 | Backend Team
Sprint 1 | Sprint 1 API testing and review | 2026-07-29 | 2026-08-02 | 5 | Testing Team
Sprint 2 | Implement billing and payment-status APIs | 2026-08-03 | 2026-08-06 | 4 | Backend Team
Sprint 2 | Implement notifications and announcements | 2026-08-04 | 2026-08-08 | 5 | Backend Team
Sprint 2 | Implement facility and inventory workflows | 2026-08-06 | 2026-08-10 | 5 | Backend Team
Sprint 2 | Sprint 2 testing and user feedback | 2026-08-09 | 2026-08-12 | 4 | Team
Final | Frontend-backend integration | 2026-08-13 | 2026-08-17 | 5 | Team
Final | System and integration testing | 2026-08-17 | 2026-08-20 | 4 | Testing Team
Final | Bug fixing and stabilization | 2026-08-19 | 2026-08-21 | 3 | Team
Final | Final documentation and demo preparation | 2026-08-20 | 2026-08-23 | 4 | Team

## Gantt Timeline
Phase | Task | Owner | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23
M1 | User identification and stakeholder analysis | Team
M1 | User research and pain-point analysis | Team
M1 | Finalize SMART user stories | Team
M2 | Refine and assign user story IDs | Team
M2 | Create and prioritize product backlog | Team
M2 | Configure Jira board and workflow | Team
M2 | Prepare overall project schedule | Team
M2 | Prepare sprint and iteration schedule | Team
M2 | Design system components | Design Team
M2 | Create UML class diagram | Design Team
M2 | Create database / ER design | Database Team
M2 | Define frontend page and route architecture | Frontend Team
M2 | Develop common UI pages | Frontend Team
M2 | Develop resident UI pages | Frontend Team
M2 | Develop manager UI pages | Frontend Team
M2 | Develop maintenance staff UI pages | Frontend Team
M2 | Connect Vue routes and redirections | Frontend Team
M2 | UI review and frontend testing | Team
M2 | Document scrum meeting minutes | Scrum Master
M2 | Prepare frontend README | Frontend Team
M2 | Compile Milestone 2 PDF report | Documentation Team
M2 | Package and validate submission | Team
Sprint 1 | Implement authentication and role APIs | Backend Team
Sprint 1 | Implement complaint management APIs | Backend Team
Sprint 1 | Implement assignment and work-status APIs | Backend Team
Sprint 1 | Sprint 1 API testing and review | Testing Team
Sprint 2 | Implement billing and payment-status APIs | Backend Team
Sprint 2 | Implement notifications and announcements | Backend Team
Sprint 2 | Implement facility and inventory workflows | Backend Team
Sprint 2 | Sprint 2 testing and user feedback | Team
Final | Frontend-backend integration | Team
Final | System and integration testing | Testing Team
Final | Bug fixing and stabilization | Team
Final | Final documentation and demo preparation | Team

## Smart socityu complaint resolu
Phase | Focus | Task | Start Date | End Date | Duration | Owner
Milestone 1 | Identify user requirements | User identification and stakeholder analysis
Milestone 1 | Identify user requirements | User research and pain-point analysis
Milestone 1 | Identify user requirements | Documentation of the user stories as per the SMART guidelines
Milestone 1 | Identify user requirements | Submission of Milestone 1
Milestone 2 | Scheduling and Designing | Preparation of Schedule for the entire project
Milestone 2 | Scheduling and Designing | Preparation of Schedule for the Scrum meetings
Milestone 2 | Scheduling and Designing | Preparation of Schedule for the Sprint and iterations
Milestone 2 | Scheduling and Designing | Preparation of Gantt Chart
Milestone 2 | Scheduling and Designing | Configuration of Jira and assigning workflow
Milestone 2 | Scheduling and Designing | Preparation of the system components
Milestone 2 | Scheduling and Designing | Preparation of the UML Class diagram
Milestone 2 | Scheduling and Designing | Designing of the Database
Milestone 2 | Scheduling and Designing | Define frontend page and route architecture
Milestone 2 | Scheduling and Designing | Develop common UI pages
Milestone 2 | Scheduling and Designing | Develop resident UI pages
Milestone 2 | Scheduling and Designing | Develop manager UI pages
Milestone 2 | Scheduling and Designing | Develop maintenance staff UI pages
Milestone 2 | Scheduling and Designing | Connect Vue routes and redirections
Milestone 2 | Scheduling and Designing | UI review and frontend testing
Milestone 2 | Scheduling and Designing | Document scrum meeting minutes
Milestone 2 | Scheduling and Designing | Prepare frontend README
Milestone 2 | Scheduling and Designing | Compile Milestone 2 PDF report
Milestone 2 | Scheduling and Designing | Package and validate submission